## Slide 1: PERT CHARTS
PROJECT EVALUATION & REVIEW TECHNIQUE

## Slide 2: Objectives
Learn how to Install EdrawMax.
Understand how to draw PERT Charts.

## Slide 3: PERT Charts
EdrawMax

## Slide 4: CHARTER 1
Question 1
Activities | Dependencies
A | 
B | 
C | A
D | B
E | C,D
PERT Chart
.

## Slide 5: CHARTER 1 (Continues…)
Question 2
Activities | Dependencies
A | 
B | A
C | A
D | A
E | A
F | E
G | D
H | G,F
I | C,H
J | B
PERT Chart
.

## Slide 6: Forward & Backward Pass
Slack, Critical Path & Project Duration

## Slide 7: CHARPTER 2
Question 1
Construct a network diagram.
Find the critical path.
Determine the duration the project is likely to take you to complete.
Data
Activities | Dependencies | Duration
A |  | 5
B |  | 6
C |  | 3
D | A | 5
E | B | 7
F | C | 4
G | D | 10
H | E | 2
I | F | 4
J | G,H,I | 6

## Slide 8: CHARPTER 2 (Continues…)
.

## Slide 9: PERT Chart
Drawing a Pert Chart using A Statement

## Slide 10: CHARPTER 3
E > B, C; F, G > D; H,I > E, F; J > I, G; K > H; B > A

## Slide 11: PERT Chart
ES, EF, LF, LS, TF, FF, IND F, INT F & TAIL AND HEAD SLACK

## Slide 12: CHAPTER 4
Data
Activities | Duration
1 – 2 | 8
1 – 3 | 7
1 – 5 | 12
2 – 3 | 4
2 – 4 | 10
3 – 4 | 3
3 – 5 | 5
3 – 6 | 10
4 – 6 | 7
5 – 6 | 4
Question 1
Calculate the Earliest Finish (EF), Eeliest Start (ES), Latest Finish (LF) and Latest Start (LS).
Compute the Total Float (TF), Free Float (FF), Independent Float (IND F) and Interfering Float (INT F).

## Slide 13: PERT Chart
To, tm, tp, te, Variance & Standard Deviation

## Slide 14: CHAPTER 5
Will cover this chapter on 19th September, 2025. Time to be communicated, and the venue still stands….. M202.