## Slide 1: Binary
Unit 2.1

## Slide 2: How To Convert a Decimal Number into Binary (Powers of 2)
To achieve this will utilize the powers of 2.
2 ^ 0 = 1
2 ^ 1 = 2
2 ^ 2 = 4
2 ^ 3 = 8
2 ^ 4 = 16
2 ^ 5 = 32
2 ^ 6 = 64
2 ^ 7 = 128
For example, let’s convert 75 into binary
128 64 32 16 8 4 2 1
0 1 0 0 1 0 1 1 = 75
Sign (+)
Magnitude

## Slide 3: How To Convert a Decimal Number into Binary (Powers of 2) (Continues…)
Let’s take another example of 339
512 256 128 64 32 16 8 4 2 1
0 1 0 1 0 1 0 0 1 1 = 339
1 = True
0 = False
Sign (+)
Magnitude

## Slide 4: How To Convert a Decimal Number into Binary Successive Division
Now, let’s use successive division to find the binary of 75
75 / 2 = 37 R 1
37 / 2 = 18 R 1
18 / 2 = 9 R 0
9 / 2 = 4 R 1
4 / 2 = 2 R 0
2 / 2 = 1 R 0
1 / 2 = 0 R 1
We now get the binary from the bottom to the top, making it:
1001011

## Slide 5: How To Add Binary Numbers
Here are some basics of addition:
0 + 0 = 0
0 + 1 = 1
1 + 0 = 1
1 + 1 = 10
1
+ 1
___
1 0 , this is the same as 1 + 1 = 2
2 / 2 = 1 R 0

## Slide 6: How To Add Binary Numbers (Continues…)
1
1
+ 1
____
1 1 This is the same as 1+1+1 = 3
3 / 2 = 1 R 1
NOTE: On the bottom we are putting the reminder (R) and carrying the number of times 2 enters into the target number.

## Slide 7: How To Add Binary Numbers (Continues…)
Let’s take an example below:
1 0 1 0 = 10
+ 1 0 0 1 = 9
________ ___
1 0 0 1 1 = 19
16 | 8 | 4 | 2 | 1 | Decimal
 | 1 | 0 | 1 | 0 | 10
 | 1 | 0 | 0 | 1 | 9
1 | 0 | 0 | 1 | 1 | 19

## Slide 8: How To Subtract Binary Numbers
Here are some basics of subtraction:
1 - 0 = 1
1 - 1 = 0
1 0 → 0 2
- 1 → 1
____
1 In base 2, will get a 2 from the
nearest value.
 | 1 | 1 | 
0 | 2 | 2 | 2
1 | 0 | 0 | 0
- |  |  | 1
0 | 1 | 1 | 1
→
8 | 4 | 2 | 1
8 |  |  | 
- |  |  | 1
 |  |  | 7

## Slide 9: 1’s & 2’s Complement
1’s Complement
Obtain 1’s complement of 1010.
NOTE: In ones complement we slip the numbers, 1 becomes 0 and 0 becomes 1.
Therefore 1’s complement of 1010 is 0101.
2’s Complement
Formular:
2’s complement = 1’s complement + 1
QUESTION: Obtain 1’s complement of 10111010.
1s complement = 01000101
2s complement = 01000110

## Slide 10: Signed Magnitude
Converting a Binary
Let’s take an example, let’s express (-6) using the signed magnitude.
What is (+6) in binary?
8 4 2 1
0 1 1 0 = +6
Negative Binary Representation
The Sign (+) will change from 0 to 1 Sign (-).
8 4 2 1
1 1 1 0
NOTE: 1 represent negative and 0 positive
Magnitude
Sign (+)
Sign (-)

## Slide 11: 2’s Complement
Negative numbers
Represent -12 in binary using the 2’s complement.
16 8 4 2 1
0 1 1 0 0 = 12
1 0 0 1 1 = 1’s complement
2’s Complement (-12)
1 0 0 1 1
+ 1
________
1 0 1 0 0 = -16 + 4 = -12
Sign (-)
Magnitude

## Slide 12: 2’s complement Subtraction
Binary Conversation
Let’s subtract 39 – (25).
Using normal math operation 39 – 25 = 14.
Convert 39 and 25 into binary.
64 32 16 8 4 2 1
0 1 0 0 1 1 1 = 39
- 0 0 1 1 0 0 1 = 25
0 0 0 1 1 1 0 = 14, Proof (8+4+12)
1’s & 2’s Complement
Find the 1’s complement 25.
1 1 0 0 1 1 0 = 25 1’s complement
Find the 2’s complement of 25.
1 1 0 0 1 1 1 = 25 2’s complement
NOTE: We are targeting 25, because in 2’s complement subtraction we change the sign of the number after the minus (-) sign, so 25 becomes -25.
0
2
1
2

## Slide 13: 2’s complement Subtraction (Continues…)
2’s complement subtraction
Finally, do the 2’s complement subtraction of 39 and 25.
0 1 0 0 1 1 1
+1 1 0 0 1 1 1
(1) 0 0 0 1 1 1 0
Verification
Is 0001110 14?
128 64 32 16 8 4 2 1
0 0 0 0 1 1 1 0
8 + 4 + 2 = 14, NOTE: In 2’s complement subtraction we add two binaries, think of it as 39 – 25 is the same as 39 + (-25).
NOTE: We have a carry 1 at the end,
but we are just ignoring it, meaning an
overflow as occurred.

## Slide 14: PERT Chart
Unit 2.2

## Slide 15: PERT Chart Example 1
Question
PERT Chart
Activities | Dependencies
A | 
B | 
C | A
D | B
E | C,D
A
B
C
D
E
1
2
3
4
5

## Slide 16: PERT Chart Example 2
Question
PERT Chart
Activities | Dependencies
A | 
B | A
C | A
D | A
E | A
F | E
G | D
H | G,F
I | C,H
J | B
1
2
A
B
C
D
3
6
F
5
E
7
G
4
H
I
8
J

## Slide 17: Question
Construct a network diagram.
Find the critical path.
Determine the duration the project is likely to take you to complete.

## Slide 18: PERT Chart Example 3
Construct a network diagram.
PERT Chart
Activities | Dependencies | Duration (Days)
A |  | 5
B |  | 3
C | A | 10
D | B | 2
E | C,D | 6
A
B
(2)
D
E
1
2
3
4
5
(5)
(10)
(6)
(3)
C
0
5
3
15
21
Eeriest Start Time (ES) = ES + Duration
Latest Start Time (LC) = LC - Duration
Critical Path (CMP) = 1 – 2 – 4 – 5
Duration of The Project = 5 + 10 + 6
= 21 Days
0
5
15
13
21

## Slide 19: PERT Chart Example 4
PERT Chart
Activities | Dependencies | Duration (Days)
A |  | 5
B |  | 6
C |  | 3
D | A | 5
E | B | 7
F | C | 4
G | D | 10
H | E | 2
I | F | 4
J | G,H,I | 6
1
2
A
B
C
D
3
6
F
5
E
7
G
4
H
I
8
J
(5)
(6)
(3)
(5)
(7)
(4)
(10)
(2)
(4)
(6)
0
5
3
6
10
7
13
20
9
26
26
20
10
5
0
18
11
16
12

## Slide 20: PERT Chart
TASK ID | TASK DESCRIPTION | TASK PRE-DESSOR (S) | TASK DURATION (HOURS)
A | Project Starts |  | 0
B | Buy Materials for A | A | 10
C | Buy Materials for B | A | 20
D | Build A | B,C | 30
E | Build B | B,C | 20
F | Finish building B | E | 40
G | Join A and B | D,F | 20
H | Finish Project | G | 0
Activities | Dependencies | Duration (Days)
A |  | 4
B |  | 3
C |  | 2
D | A | 5
E | A,B | 6
F | C | 3
G | D | 4
H | E | 2
I | F | 3
J | G,H,I | 5
TASK 1
TASK 2

## Slide 21: TASK 1
STECTCH
START
FINISH
A
B
C
D
E
F
G
H
I
I

## Slide 22: TASK 1 (Continues…)
PERT CHART
START
FINISH
A
B
C
D
E
F
G
H
I
J
4
3
2
0
0
0
4
3
2
4
4
2
5
6
3
9
10
5
9
10
5
4
2
3
13
12
8
13
5
18
18
0
18
18
13
13
13
13
10
9
11
9
11
10
7
5
4
4
5
7
5
2
0
5
0
0
0
2
1
1
0
5
5
A – D – G – J
0
KEY
Activity Time (t)
Forward Pass
Backward Pass
Slack
Critical Path

## Slide 23: TASK 2
SKETCH
A
B
C
E
F
G
H
D

## Slide 24: TASK 2 (Continues…)
PERT CHART
A
H
B
C
D
E
F
G
10
20
30
40
20
20
0
0
0
10
20
20
20
50
40
80
40
100
80
100
100
100
100
80
60
60
80
40
50
40
40
30
20
20
G – H
20
30
20
30
0
0
20
20
Project Starts
Buy materials for A
Buy materials for B
Build A
Build B
Finish building B
Join A and B
Finish Project
KEY
Activity Time (t)
Forward Pass
Backward Pass
Slack
Critical Path

## Slide 25: PERT CHART GUIDE
Activity | A | B | C | D | E | F | G
Immediate Predecessors |  |  | A | A,B | D | C,E | E
Expected Time (weeks) | 7 | 9 | 12 | 8 | 9 | 6 | 5
OBJECTIVES
1. Construct a project network
2. Perform forward and back passes
3. Determine project completion time
4. Calculate slack values
5. State the critical path
A | ES | EF
t | LS | LF
KEY
A. Activities
t. Expected duration or Activity Time
ES. Earliest Start Time
EF. Earliest Finish Time
LS. Latest Start Time
LF. Latest Finish Time

## Slide 26: Steps When Creating a PERT Chart
Create a draft or sketch.
START
A
B
C
D
E
F
G
FINISH
NOTE: Since F and G have nor predecessors they go to finish.

## Slide 27: Steps When Creating a PERT Chart (Continues…)
Creating the actual PERT Chart.
A
FINISH
START
B
C
D
E
F
G
7
9
12
8
9
6
5
Activity Time (t)
KEY

## Slide 28: Steps When Creating a PERT Chart (Continues…)
Calculating the Forward Pass: EF = ES + t
A
FINISH
START
B
C
D
E
F
G
7
9
12
8
9
6
5
Activity Time (t)
KEY
9
0
7
0
9
7
19
0
17
17
26
26
31
26
32
32
Forward Pass
NOTE: D is dependent on A and B to start
and in Forward Pass we consider the highest EF (9)
NOTE: F is dependent on C and E to start
and in Forward Pass we consider the highest EF (26)
NOTE: FINISH is dependent on F and G to stop
and in Forward Pass we consider the highest EF (32)

## Slide 29: Steps When Creating a PERT Chart (Continues…)
Calculating the Backward Pass: LS = LF - t
A
FINISH
START
B
C
D
E
F
G
7
9
12
8
9
6
5
Activity Time (t)
KEY
9
0
7
0
9
7
19
0
17
17
26
26
31
26
32
32
Forward Pass
32
32
32
27
26
26
17
26
14
17
9
9
0
9
2
0
Backward Pass
NOTE: E is dependent on F and G to start
and in Backward Pass we consider the lowest LF (26)
NOTE: A is dependent on C and D to start
and in Backward Pass we consider the lowest LF (9)
NOTE: START is dependent on A and B to start
and in Backward Pass we consider the lowest LF (0)

## Slide 30: Steps When Creating a PERT Chart (Continues…)
Calculating the Slack: LS – ES or LF - EF
A
FINISH
START
B
C
D
E
F
G
7
9
12
8
9
6
5
Activity Time (t)
KEY
9
0
7
0
9
7
19
0
17
17
26
26
31
26
32
32
Forward Pass
32
32
32
27
26
26
17
26
14
17
9
9
0
9
2
0
Backward Pass
2
7
0
0
0
0
1
Slack

## Slide 31: Steps When Creating a PERT Chart (Continues…)
Identifying the Critical Path: slack = 0
A
FINISH
START
B
C
D
E
F
G
7
9
12
8
9
6
5
Activity Time (t)
KEY
9
0
7
0
9
7
19
0
17
17
26
26
31
26
32
32
Forward Pass
32
32
32
27
26
26
17
26
14
17
9
9
0
9
2
0
Backward Pass
2
7
0
0
0
0
1
Slack
Critical Path = B – D – E – F
Critical Path

## Slide 32: Steps When Creating a PERT Chart (Continues…)
Final PERT Chart
A
FINISH
START
B
C
D
E
F
G
7
9
12
8
9
6
5
Activity Time (t)
KEY
9
0
7
0
9
7
19
0
17
17
26
26
31
26
32
32
Forward Pass
32
32
32
27
26
26
17
26
14
17
9
9
0
9
2
0
Backward Pass
2
7
0
0
0
0
1
Slack
B – D – E – F
Critical Path