## Slide 1: PERT CHARTS
PROJECT EVALUATION & REVIEW TECHNIQUE

## Slide 2: Objectives
Learn how to Install EdrawMax.
Understand how to draw PERT Charts.

## Slide 3: PERT Charts
EdrawMax

## Slide 4: CHARTER 1
Question 1
Activities | Dependencies
A | 
B | 
C | A
D | B
E | C,D
PERT Chart
.

## Slide 5: CHARTER 1 (Continues…)
Question 2
Activities | Dependencies
A | 
B | A
C | A
D | A
E | A
F | E
G | D
H | G,F
I | C,H
J | B
PERT Chart
.

## Slide 6: Forward & Backward Pass
Slack, Critical Path & Project Duration

## Slide 7: CHARPTER 2
Question 1
Construct a network diagram.
Find the critical path.
Determine the duration the project is likely to take you to complete.
Data
Activities | Dependencies | Duration
A |  | 5
B |  | 6
C |  | 3
D | A | 5
E | B | 7
F | C | 4
G | D | 10
H | E | 2
I | F | 4
J | G,H,I | 6

## Slide 8: CHARPTER 2 (Continues…)
.

## Slide 9: PERT Chart
Drawing a Pert Chart using A Statement

## Slide 10: CHARPTER 3
Question 1
E > B, C; F, G > D; H,I > E, F; J > I, G; K > H; B > A
Activities | Dependencies
A | 
B | A
C | 
D | 
E | B,C
F | D
G | D
H | E,F
I | E,F
J | I,G
K | H

## Slide 11: CHARPTER 3 (Continues…)

## Slide 12: PERT Chart
ES, EF, LF, LS, TF, FF, IND F, INT F & TAIL AND HEAD SLACK

## Slide 13: CHAPTER 4
Data
Activities | Duration
1 – 2 | 8
1 – 3 | 7
1 – 5 | 12
2 – 3 | 4
2 – 4 | 10
3 – 4 | 3
3 – 5 | 5
3 – 6 | 10
4 – 6 | 7
5 – 6 | 4
Question 1
Calculate the Earliest Finish (EF), Eeliest Start (ES), Latest Finish (LF) and Latest Start (LS).
Compute the Total Float (TF), Free Float (FF), Independent Float (IND F) and Interfering Float (INT F).

## Slide 14: CHAPTER 4 (Continues…)

## Slide 15: CHAPTER 4 (Continues…)
Activities | ES | Duration (t) | EF = ES + t
1 – 2 | 0 | 8 | 8
1 – 3 | 0 | 7 | 7
1 – 5 | 0 | 12 | 12
2 – 3 | 8 | 4 | 12
2 – 4 | 8 | 10 | 18
3 – 4 | 12 | 3 | 15
3 – 5 | 12 | 5 | 17
3 – 6 | 12 | 10 | 22
4 – 6 | 18 | 7 | 25
5 – 6 | 17 | 4 | 21

## Slide 16: CHAPTER 4 (Continues…)
Activities | LF | Duration (t) | LS = LF - t
1 – 2 | 8 | 8 | 0
1 – 3 | 15 | 7 | 8
1 – 5 | 21 | 12 | 9
2 – 3 | 15 | 4 | 11
2 – 4 | 18 | 10 | 8
3 – 4 | 18 | 3 | 15
3 – 5 | 21 | 5 | 16
3 – 6 | 25 | 10 | 15
4 – 6 | 25 | 7 | 18
5 – 6 | 25 | 4 | 21

## Slide 17: CHAPTER 4 (Continues…)
Activities | LS | ES | TF = LS – ES
1 – 2 | 0 | 0 | 0
1 – 3 | 8 | 0 | 8
1 – 5 | 9 | 0 | 9
2 – 3 | 11 | 8 | 3
2 – 4 | 8 | 8 | 0
3 – 4 | 15 | 12 | 3
3 – 5 | 16 | 12 | 4
3 – 6 | 15 | 12 | 3
4 – 6 | 18 | 18 | 0
5 – 6 | 21 | 17 | 4

## Slide 18: CHAPTER 4 (Continues…)
Activities | Tail Slack (T) | Head Slack (H) | TF | FF = TF – H | IND = FF – T | IND F = TF - FF
1 – 2 | 0 | 0 | 0 | 0 | 0 | 0
1 – 3 | 0 | 3 | 8 | 5 | 5 | 3
1 – 5 | 0 | 4 | 9 | 5 | 5 | 4
2 – 3 | 0 | 3 | 3 | 0 | 0 | 3
2 – 4 | 0 | 0 | 0 | 0 | 0 | 0
3 – 4 | 3 | 0 | 3 | 3 | 0 | 0
3 – 5 | 3 | 4 | 4 | 0 | -3 | 4
3 – 6 | 3 | 0 | 3 | 3 | 0 | 0
4 – 6 | 0 | 0 | 0 | 0 | 0 | 0
5 – 6 | 4 | 0 | 4 | 4 | 0 | 0

## Slide 19: PERT Chart
To, tm, tp, te, Variance & Standard Deviation

## Slide 20: CHAPTER 5
Data
Activities | to | tp | tm
1 – 2 | 1 | 3 | 2
1 – 3 | 5 | 7 | 6
1 – 4 | 3 | 7 | 5
2 – 5 | 5 | 9 | 7
3 – 5 | 2 | 6 | 4
5 – 6 | 4 | 6 | 5
4 – 7 | 4 | 8 | 6
6 – 7 | 2 | 4 | 3
Question 1
Draw the corresponding network diagram.
Compute the expected duration for each activity.
Calculate the expected variance of each activity.
Determine the expected critical path variance.
Compute the standard deviation of each activity.

## Slide 21: CHAPTER 5 (Continues…)
Activities | to | tp | tm | 4tm | Te = (to + tp + 4tm) ÷ 6 | σ = (tp – to) ÷ 6 | σ²
1 – 2 | 1 | 3 | 2 | 4(2) = 8 | (1 + 3 + 8) ÷ 6 = 2 | (3 – 1) ÷ 6 = 0.33 | 0.10
1 – 3 | 5 | 7 | 6 | 4(6) = 24 | (5 + 7 + 24) ÷ 6 = 6 | (7 – 5) ÷ 6 = 0.33 | 0.10
1 – 4 | 3 | 7 | 5 | 4(5) = 20 | (3 + 7 + 20) ÷ 6 = 5 | (7 – 3) ÷ 6 = 0.66 | 0.43
2 – 5 | 5 | 9 | 7 | 4(7) = 28 | (5 + 9 + 28) ÷ 6 = 7 | (9 – 5) ÷ 6 = 0.66 | 0.43
3 – 5 | 2 | 6 | 4 | 4(4) = 16 | (2 + 6 + 16) ÷ 6 = 4 | (6 – 2) ÷ 6 = 0.66 | 0.43
5 – 6 | 4 | 6 | 5 | 4(5) = 20 | (4 + 6 + 20) ÷ 6 = 5 | (6 – 4) ÷ 6 = 0.33 | 0.10
4 – 7 | 4 | 8 | 6 | 4(6) = 24 | (4 + 8 + 24) ÷ 6 = 6 | (8 – 4) ÷ 6 = 0.66 | 0.43
6 – 7 | 2 | 4 | 3 | 4(3) = 12 | (2 + 4 + 12) ÷ 6 = 3 | (4 – 2) ÷ 6 = 0.33 | 0.10

## Slide 22: CHAPTER 5 (Continues…)

## Slide 23: PERT Charts
Real World Application in System Vulnerability Assessment

## Slide 24: CHAPTER 6
This chapter will be covered on Monday, to finish our PERT Chart revisions, the venue is still M202 and time will be communicated through a WhatsApp voting poll.