## Slide 1: PERT Chart
Unit 2.2

## Slide 2: Benefits of a PERT Chart
Program Evaluation and Review Technique (PERT) chart is a project management tool used to plan, schedule, and coordinate tasks within a project by visually mapping activities and their dependencies.
Benefits of a PERT Chart include;
Visualization of dependencies
Critical path identification
Effective time management
Risk management
Clear communication
Resource optimization
Project monitoring and control

## Slide 3: Challenges of PERT Charts
Limitation
The accuracy of the PERT chart depends heavily on the quality of the estimates for the activity times.
Key Features
Optimistic time (O/to) – Shortest duration if everything goes perfectly.
Pessimistic time (P/tp) – Longest possible duration if challenges occur.
Most likely time (M/tm) – Expected duration under normal conditions.
Critical path - The longest path through the network, which determines the shortest time for project completion.

## Slide 4: Software for developing PERT Charts
LucidChart
SmartDraw
EdrawMax
Creately
Microsoft Visio

## Slide 5: PERT Chart Example 1
Question
PERT Chart
Activities | Dependencies
A | 
B | 
C | A
D | B
E | C,D
A
B
C
D
E
1
2
3
4
5

## Slide 6: PERT Chart Example 2
Question
PERT Chart
Activities | Dependencies
A | 
B | A
C | A
D | A
E | A
F | E
G | D
H | G,F
I | C,H
J | B
1
2
A
B
C
D
3
6
F
5
E
7
G
4
H
I
8
J

## Slide 7: PERT Chart Example 2
Question
PERT Chart
Activities | Dependencies
A | 
B | A
C | A
D | A
E | A
F | E
G | D
H | G,F
I | C,H
J | B
1
2
A
B
C
D
3
6
F
5
E
7
G
4
H
I
8
J

## Slide 8: Question
Construct a network diagram.
Find the critical path.
Determine the duration the project is likely to take you to complete.

## Slide 9: PERT Chart Example 3
Construct a network diagram.
PERT Chart
Activities | Dependencies | Duration (Days)
A |  | 5
B |  | 3
C | A | 10
D | B | 2
E | C,D | 6
A
B
(2)
D
E
1
2
3
4
5
(5)
(10)
(6)
(3)
C
0
5
3
15
21
Earliest Finish Time (EF) = ES + Duration
Latest Start Time (LS) = LF - Duration
Critical Path (CMP) = 1 – 2 – 4 – 5
Duration of The Project = 5 + 10 + 6
= 21 Days
0
5
15
13
21

## Slide 10: PERT Chart Example 4
PERT Chart
Activities | Dependencies | Duration (Days)
A |  | 5
B |  | 6
C |  | 3
D | A | 5
E | B | 7
F | C | 4
G | D | 10
H | E | 2
I | F | 4
J | G,H,I | 6
1
2
A
B
C
D
3
6
F
5
E
7
G
4
H
I
8
J
(5)
(6)
(3)
(5)
(7)
(4)
(10)
(2)
(4)
(6)
0
5
3
6
10
7
13
20
9
26
26
20
10
5
0
18
11
16
12
Critical Path (CMP) = 1 – 2 – 5 – 8 – 9
Total Duration = 5 + 5 + 10 + 6
= 26
Slack = 0
Slack = 0
Slack = 0
Slack = 0
Slack = 0
Slack = 9
Slack = 9
Slack = 5
Slack = 5

## Slide 11: PERT Chart
TASK ID | TASK DESCRIPTION | TASK PRE-DESSOR (S) | TASK DURATION (HOURS)
A | Project Starts |  | 0
B | Buy Materials for A | A | 10
C | Buy Materials for B | A | 20
D | Build A | B,C | 30
E | Build B | B,C | 20
F | Finish building B | E | 40
G | Join A and B | D,F | 20
H | Finish Project | G | 0
Activities | Dependencies | Duration (Days)
A |  | 4
B |  | 3
C |  | 2
D | A | 5
E | A,B | 6
F | C | 3
G | D | 4
H | E | 2
I | F | 3
J | G,H,I | 5
TASK 1
TASK 2

## Slide 12: TASK 1
STECTCH
START
FINISH
A
B
C
D
E
F
G
H
I
I

## Slide 13: TASK 1 (Continues…)
PERT CHART
START
FINISH
A
B
C
D
E
F
G
H
I
J
4
3
2
0
0
0
4
3
2
4
4
2
5
6
3
9
10
5
9
10
5
4
2
3
13
12
8
13
5
18
18
0
18
18
13
13
13
13
10
9
11
9
11
10
7
5
4
4
5
7
5
2
0
5
0
0
0
2
1
1
0
5
5
A – D – G – J
0
KEY
Activity Time (t)
Forward Pass
Backward Pass
Slack
Critical Path
Total Duration = 4 + 5 + 4 + 5
= 18 days

## Slide 14: PERT CHART GUIDE
Activity | A | B | C | D | E | F | G
Immediate Predecessors |  |  | A | A,B | D | C,E | E
Expected Time (weeks) | 7 | 9 | 12 | 8 | 9 | 6 | 5
OBJECTIVES
1. Construct a project network
2. Perform forward and back passes
3. Determine project completion time
4. Calculate slack values
5. State the critical path
A | ES | EF
t | LS | LF
KEY
A. Activities
t. Expected duration or Activity Time
ES. Earliest Start Time
EF. Earliest Finish Time
LS. Latest Start Time
LF. Latest Finish Time

## Slide 15: Steps When Creating a PERT Chart
Create a draft or sketch.
START
A
B
C
D
E
F
G
FINISH
NOTE: Since F and G have nor predecessors they go to finish.

## Slide 16: Steps When Creating a PERT Chart (Continues…)
Creating the actual PERT Chart.
A
FINISH
START
B
C
D
E
F
G
7
9
12
8
9
6
5
Activity Time (t)
KEY

## Slide 17: Steps When Creating a PERT Chart (Continues…)
Calculating the Forward Pass: EF = ES + t
A
FINISH
START
B
C
D
E
F
G
7
9
12
8
9
6
5
Activity Time (t)
KEY
9
0
7
0
9
7
19
0
17
17
26
26
31
26
32
32
Forward Pass
NOTE: D is dependent on A and B to start
and in Forward Pass we consider the highest EF (9)
NOTE: F is dependent on C and E to start
and in Forward Pass we consider the highest EF (26)
NOTE: FINISH is dependent on F and G to stop
and in Forward Pass we consider the highest EF (32)

## Slide 18: Steps When Creating a PERT Chart (Continues…)
Calculating the Backward Pass: LS = LF - t
A
FINISH
START
B
C
D
E
F
G
7
9
12
8
9
6
5
Activity Time (t)
KEY
9
0
7
0
9
7
19
0
17
17
26
26
31
26
32
32
Forward Pass
32
32
32
27
26
26
17
26
14
17
9
9
0
9
2
0
Backward Pass
NOTE: E is dependent on F and G to start
and in Backward Pass we consider the lowest LF (26)
NOTE: A is dependent on C and D to start
and in Backward Pass we consider the lowest LF (9)
NOTE: START is dependent on A and B to start
and in Backward Pass we consider the lowest LF (0)

## Slide 19: Steps When Creating a PERT Chart (Continues…)
Calculating the Slack: LS – ES or LF - EF
A
FINISH
START
B
C
D
E
F
G
7
9
12
8
9
6
5
Activity Time (t)
KEY
9
0
7
0
9
7
19
0
17
17
26
26
31
26
32
32
Forward Pass
32
32
32
27
26
26
17
26
14
17
9
9
0
9
2
0
Backward Pass
2
7
0
0
0
0
1
Slack

## Slide 20: Steps When Creating a PERT Chart (Continues…)
Identifying the Critical Path: slack = 0
A
FINISH
START
B
C
D
E
F
G
7
9
12
8
9
6
5
Activity Time (t)
KEY
9
0
7
0
9
7
19
0
17
17
26
26
31
26
32
32
Forward Pass
32
32
32
27
26
26
17
26
14
17
9
9
0
9
2
0
Backward Pass
2
7
0
0
0
0
1
Slack
Critical Path = B – D – E – F
Critical Path
Total Duration = 9 + 8 + 9 + 6
= 32

## Slide 21: Steps When Creating a PERT Chart (Continues…)
Final PERT Chart
A
FINISH
START
B
C
D
E
F
G
7
9
12
8
9
6
5
Activity Time (t)
KEY
9
0
7
0
9
7
19
0
17
17
26
26
31
26
32
32
Forward Pass
32
32
32
27
26
26
17
26
14
17
9
9
0
9
2
0
Backward Pass
2
7
0
0
0
0
1
Slack
B – D – E – F
Critical Path
Total Duration = 9 + 8 + 9 + 6
= 32

## Slide 22: EXAMPLE 5
E > B, C; F, G > D; H,I > E, F; J > I, G; K > H; B > A
Activities | Predecessors
A | 
B | A
C | 
D | 
E | B, C
F | D
G | D
H | E, F
I | E, F
J | I, G
K | H
1
2
3
4
5
6
7
8
A
B
C
D
E
F
G
H
I
J
K

## Slide 23: EXAMPLE 6
.
1
A
2
B
C
F
D
E
G
H
3
5
4

## Slide 24: TASK 3
Calculate the Earliest Finish (EF), Eeliest Start (ES), Latest Finish (LF) and Latest Start (LS).
Compute the Total Float (TF), Free Float (FF), Independent Float (IND F) and Interfering Float (INT F).

## Slide 25: TASK 3 (CONTINUES…) – NETWORK DIAGRAM
Activities | Duration
1 – 2 | 8
1 – 3 | 7
1 – 5 | 12
2 – 3 | 4
2 – 4 | 10
3 – 4 | 3
3 – 5 | 5
3 – 6 | 10
4 – 6 | 7
5 – 6 | 4
1
2
3
5
4
6
8
7
12
4
10
3
5
10
4
7
8
12
17
18
25
25
18
21
15
8
0
0
Slack = 0
Slack = 3
Slack = 0
Slack = 4
Critical Path = 1 – 2 – 4 – 6
Slack = 0
Slack = 0

## Slide 26: TASK 3 (CONTINUES…) – ES, EF, LF, LS & TF
Activities | ES | Duration | EF (ES + D)
1 – 2 | 0 | 8 | 8
1 – 3 | 0 | 7 | 7
1 – 5 | 0 | 12 | 12
2 – 3 | 8 | 4 | 12
2 – 4 | 8 | 10 | 18
3 – 4 | 12 | 3 | 15
3 – 5 | 12 | 5 | 17
3 – 6 | 12 | 10 | 22
4 – 6 | 18 | 7 | 25
5 – 6 | 17 | 4 | 21
Activities | LF | Duration | LS (LF - D)
1 – 2 | 8 | 8 | 0
1 – 3 | 15 | 7 | 8
1 – 5 | 21 | 12 | 9
2 – 3 | 15 | 4 | 11
2 – 4 | 18 | 10 | 8
3 – 4 | 18 | 3 | 15
3 – 5 | 21 | 5 | 16
3 – 6 | 25 | 10 | 15
4 – 6 | 25 | 7 | 18
5 – 6 | 25 | 4 | 21
LS | ES | TF (LS - ES)
0 | 0 | 0
8 | 0 | 8
9 | 0 | 9
11 | 8 | 3
8 | 8 | 0
15 | 12 | 3
16 | 12 | 4
15 | 12 | 3
18 | 18 | 0
21 | 17 | 4

## Slide 27: TASK 3 (CONTINUES…) – FF, IND F & INT F
Activities | T | H | TF | FF (TF – H) | IND F (FF – T) | INT F (TF – FF)
1 – 2 | 0 | 0 | 0 | 0 | 0 | 0
1 – 3 | 0 | 3 | 8 | 5 | 5 | 3
1 – 5 | 0 | 4 | 9 | 5 | 5 | 4
2 – 3 | 0 | 3 | 3 | 0 | 0 | 3
2 – 4 | 0 | 0 | 0 | 0 | 0 | 0
3 – 4 | 3 | 0 | 3 | 3 | 0 | 0
3 – 5 | 3 | 4 | 4 | 0 | -3 | 4
3 – 6 | 3 | 0 | 3 | 3 | 0 | 0
4 – 6 | 0 | 0 | 0 | 0 | 0 | 0
5 – 6 | 4 | 0 | 4 | 4 | 0 | 0

## Slide 28: TASK 4
Activities | Duration
1 – 2 | 13
1 – 3 | 12
2 – 4 | 2
3 – 4 | 8
2 – 5 | 15
4 – 5 | 2
1
2
3
5
4
2
13
12
2
8
5
15
13
12
28
20
26
28
18
13
0
0
Slack = 0
Slack = 0
Slack = 6
Critical Path = 1 – 2 – 5
Slack = 6
Slack = 0
Total Duration = 13 + 15
= 28

## Slide 29: TASK 4 (CONTINUES…) – ES, EF, LF, LS & TF
Activities | ES | Duration | EF (ES + D)
1 – 2 | 0 | 13 | 13
1 – 3 | 0 | 12 | 12
2 – 4 | 13 | 2 | 15
3 – 4 | 12 | 8 | 20
2 – 5 | 13 | 15 | 28
4 – 5 | 20 | 2 | 22
Activities | LF | Duration | LS (LF - D)
1 – 2 | 13 | 13 | 0
1 – 3 | 18 | 12 | 6
2 – 4 | 26 | 2 | 24
3 – 4 | 26 | 8 | 18
2 – 5 | 28 | 15 | 13
4 – 5 | 28 | 2 | 26
LS | ES | TF (LS - ES)
0 | 0 | 0
6 | 0 | 6
24 | 13 | 11
18 | 12 | 6
13 | 13 | 0
26 | 20 | 6

## Slide 30: TASK 4 (CONTINUES…) – FF, IND F & INT F
Activities | T | H | TF | FF (TF – H) | IND F (FF – T) | INT F (TF – FF)
1 – 2 | 0 | 0 | 0 | 0 | 0 | 0
1 – 3 | 0 | 6 | 6 | 0 | 0 | 6
2 – 4 | 0 | 6 | 11 | 5 | 5 | 6
3 – 4 | 6 | 6 | 6 | 0 | -6 | 6
2 – 5 | 0 | 0 | 0 | 0 | 0 | 0
4 – 5 | 6 | 0 | 6 | 6 | 0 | 0
UP NEXT… EXAMPLE 7

## Slide 31
Activity | Optimistic (O or to) | Pessimistic (P or tp) | Most Likely (M or tm) | 4tm | Te = (to + 4tm + tp) / 6 | σ = (tp – to) / 6 | σ²
1 – 2 | 1 | 3 | 2 | 4(2) =8 | (1 + 8 + 3) / 6 = 2 | (3 – 1) / 6 = 0.33 | 0.10
1 – 3 | 5 | 7 | 6 | 4(6) = 24 | (5 + 12 + 7) / 6 = 6 | (7 – 5) / 6 = 0.33 | 0.10
1 – 4 | 3 | 7 | 5 | 4(5) = 20 | (3 + 20 + 7) / 6 = 5 | (7 – 3) / 6 = 0.66 | 0.43
2 – 5 | 5 | 9 | 7 | 4(7) = 28 | (5 + 28 + 9) / 6 = 7 | (9 – 5) / 6 = 0.66 | 0.43
3 – 5 | 2 | 6 | 4 | 4(4) = 16 | (2 + 16 + 6) / 6 = 4 | (6 – 2) / 6 = 0.66 | 0.43
5 – 6 | 4 | 6 | 5 | 4(5) = 20 | (4 + 20 + 6) / 6 = 5 | (6 – 4) / 6 = 0.33 | 0.10
4 – 7 | 4 | 8 | 6 | 4(6) = 24 | (4 + 24 + 8) / 6 = 6 | (8 – 4) / 6 = 0.66 | 0.43
6 – 7 | 2 | 4 | 3 | 4(3) = 12 | (2 + 12 + 4) /6 = 3 | (4 – 2) / 6 = 0.33 | 0.10
1
2
3
4
5
6
7
6
4
5
3
6
5
2
7
0
6
2
5
10
15
18
18
15
10
12
3
6
0
Slack = 0
Slack = 0
Slack = 0
Slack = 0
Slack = 0
Slack = 1
Slack = 7
Critical Path = 1 – 3 – 5 – 6 – 7
Critical Variance = 0.10 + 0.43 + 0.10 + 0.10
= 0.73
Total Duration = 6 + 4 + 5 + 3
= 18

## Slide 32
Activity | Optimistic (O or to) | Pessimistic (P or tp) | Most Likely (M or tm) | 4tm | Te = to + 4tm + tp | σ = (tp – to) / 6 | σ²
1 – 2 | 3 | 15 | 6 | 4(6) = 24 | (3 + 24 + 15) / 6 = 7 | (15 – 3) / 6 = 2 | 4
2 – 3 | 2 | 14 | 5 | 4(5) = 20 | (2 + 20 + 14) / 6 = 6 | (14 – 2) / 6 = 2 | 4
1 – 4 | 6 | 30 | 12 | 4(12) = 48 | (6 + 48 + 30) / 6 = 14 | (30 – 6) / 6 = 4 | 16
2 – 5 | 2 | 8 | 5 | 4(5) = 20 | (2 + 20 + 8) / 6 = 5 | (8 – 2) / 6 = 1 | 1
2 – 6 | 5 | 17 | 11 | 4(11) = 44 | (5 + 44 + 17) / 6 = 11 | (17 – 5) / 6 = 2 | 4
3 – 6 | 3 | 15 | 6 | 4(6) = 24 | (3 + 24 + 15) / 6 = 7 | (15 – 3) / 6 = 2 | 4
4 – 7 | 3 | 27 | 9 | 4(9) = 36 | (3 + 36 + 27) / 6 = 11 | (27 – 3) / 6 = 4 | 16
5 – 7 | 1 | 7 | 4 | 4(4) = 16 | (1 + 16 + 7) / 6 = 4 | (7 – 1) / 6 = 1 | 1
6 – 7 | 2 | 8 | 5 | 4(5) = 20 | (2 + 20 + 8) / 6 = 5 | (8 – 2) / 6 = 1 | 1
1
4
7
0
0
Slack = 0
Critical Path = 1 – 4 – 7
Critical Variance = 16 + 16
= 32
2
3
5
6
7
6
14
5
11
7
11
4
5
7
14
13
20
12
25
25
20
21
14
13
7
Slack = 0
Slack = 0
Slack = 0
Slack = 0
Slack = 0
Slack = 9
Total Duration = 14 + 11
= 25

## Slide 33: TASK 5
Activity | O | P | M | Dependences
Identify compromised systems | 1 | 2 | 3 | None
Patch vulnerabilities | 2 | 4 | 6 | Identify compromised vulnerabilities
Secure User Accounts | 1 | 4 | 2 | Patch vulnerabilities
Restore data | 3 | 8 | 5 | Patch vulnerabilities
Implement additional controls | 2 | 5 | 3 | Secure User Accounts
Revise Policies | 1 | 3 | 2 | Identify compromised systems
Final audit and testing | 2 | 4 | 3 | Implement additional controls, restore data

## Slide 34: TASK 5 (Continues…)
 |  | Dependence |  | Activity | to | tp | tm | 4tm | Te | σ | σ²
1 | Identify Compromised Systems |  |  |  |  |  |  |  |  |  | 
2 | Path Vulnerability | 1 |  | 1 – 2 | 1 | 2 | 3 | 12 | 2.5 | 0.16 | 0.02
3 | Secure User Accounts | 2 |  | 2 – 3 | 2 | 4 | 6 | 24 | 5 | 0.33 | 0.10
4 | Restore Data | 2 |  | 2 – 4 | 1 | 4 | 2 | 8 | 2.1 | 0.5 | 0.25
5 | Implement additional Controls | 3 |  | 3 – 5 | 3 | 8 | 5 | 20 | 5.1 | 0.83 | 0.68
6 | Revise polices | 1 |  | 1 – 6 | 2 | 5 | 3 | 12 | 3.1 | 0.5 | 0.25
7 | Final Audit and Testing | 5,4 |  | 4 – 7 | 1 | 3 | 2 | 8 | 2 | 0.33 | 0.10
 |  |  |  | 5 – 7 | 2 | 4 | 3 | 12 | 3 | 0.33 | 0.10

## Slide 35
1
2
6
3
4
5
7
2.5
5
2.1
5.1
3.1
2
3
0
2.5
3.1
4.6
7.5
12.6
15.6
15.6
12.6
7.5
2.5
13.6
15.6
0
Slack = 0
Slack = 0
Slack = 0
Slack = 0
Slack = 0
Slack = 9
Slack = 12.5
Critical Path = 1 – 2 – 3 – 5 – 7
Critical Variance = 0.02 + 0.10 + 0.68 0.10
= 0.9
Total Duration = 2.5 + 5 + 5.1 + 3
= 15.6

## Slide 36
 | ACTIVITY | DEPENDANCE |  | ACTIVITIES
1 | Root cause analysis |  |  | 1 – 2
2 | Patch development | Root cause analysis |  | 2 – 3
3 | Pact testing | Patch development |  | 3 – 5
4 | Schedule Maintenance | Pact testing |  | 3 – 4
5 | Deploy patch | Pact testing |  | 4 – 5
6 | Validate remediation | Deploy patch |  | 5 – 6
7 | Update documentation | Validate remediation |  | 6 – 7
8 | Notify stakeholders | Update documentation, Deploy patch |  | 7 – 8 5 – 8
1
2
3
4
5
6
7
8

## Slide 37: TEST 2
ANSWERS

## Slide 38: BINARY
Question one
An overflow counts for about 23% according to the CVSS of the attack and therefore, requires deep knowledge and understanding in order to easily identify and mitigate it as a vulnerability. This introduces one’s and two’s compliment numbers in binary number system which the computer is believed to be using.
Add the following numbers in two’s compliment using 8 bits. Determine whether an overflow has occurred. Show all your working. [6 Marks]

## Slide 39: BINARY (Continues…)
-47 and 19
-47 + 19 or 19 – 47 = -28
128 64 32 16 8 4 2 1
0 0 0 1 0 0 1 1 = 19
0 0 1 0 1 1 1 1 = 47
1 1 0 1 0 0 0 0 = 47’s 1’s compliment
1
+
1 1 0 1 0 0 0 1 = 47’s 2’s compliment
19 + (-47)
0 0 0 1 0 0 1 1 = 19
1 1 0 1 0 0 0 1 = 47’s 2’s comp.
+
1 1 1 0 0 1 0 0

## Slide 40: BINARY (Continues…)
98 and 74
98 + 74 = 172
128 64 32 16 8 4 2 1
0 1 1 0 0 0 1 0 = 98
0 1 0 0 1 0 1 0 = 74
+
1 0 1 0 1 1 0 0 = 172

## Slide 41: BINARY (Continues…)
Add the following numbers in one’s compliment using 8 bits. Determine whether an overflow has occurred. [6 Marks]
25 and -56
25 + (-56) = -31
128 64 32 16 8 4 2 1
0 0 0 1 1 0 0 1 = 25
0 0 1 1 1 0 0 0 = 56
1 1 0 0 0 1 1 1 = 56’s 1’s comp.
0 0 0 1 1 0 0 1 = 25
+
1 1 0 0 0 1 1 1 = 56’s 1’s comp.
1 1 1 0 0 0 0 0 = -31

## Slide 42: BINARY (Continues…)
-77 and -77
-77 + (-77) = -154
128 64 32 16 8 4 2 1
0 1 0 0 1 1 0 1 = 77
1 0 1 1 0 0 1 0 = 77’s 1’s compliment
+
1 0 1 1 0 0 1 0 = 77’s 1’s comp.
1 0 1 1 0 0 1 0 = 77’s 1’s comp.
(1) 0 1 1 0 0 1 0 0
An overflow as occurred

## Slide 43: BINARY (Continues…)
Subtract the following numbers in one’s compliment using 8 bits. Determine whether an overflow has occurred.
66 – (-78)
128 64 32 16 8 4 2 1
0 1 0 0 0 0 1 0 = 66
0 1 0 0 1 1 1 0 = 78
1 0 1 1 0 0 0 1 = 78’s 1’s compliment
0 1 0 0 0 0 1 0 = 66
1 0 1 1 0 0 0 1 = 78’s 1’s comp.
-
(1) 0 0 1 0 0 0 1
2
0
0
2
1
2
An overflow as occurred

## Slide 44: BINARY (Continues…)
72 - 25
128 64 32 16 8 4 2 1
0 1 0 0 1 0 0 0 = 72
0 0 0 1 1 0 0 1 = 25
-
0 0 1 0 1 1 1 1 = 47
0
2
1
2
1
2
0
2
1
2
1
2

## Slide 45: BINARY (Continues…)
Subtract the following numbers in two’s compliment using an octet. Determine whether an overflow has occurred. [6 Marks]
70 – 32
70 + (-32) = 38
128 64 32 16 8 4 2 1
0 1 0 0 0 1 1 0 = 70
0 0 1 0 0 0 0 0 = 32
1 1 0 1 1 1 1 1 = 32’s 1’s comp.
1
+
1 1 1 0 0 0 0 0 = 32’s 2’s comp.
0 1 0 0 0 1 1 0 = 70
1 1 1 0 0 0 0 0 = 32’s 2’s comp.
+
(1) 0 0 1 0 0 1 1 0 = 38
An overflow as occurred

## Slide 46: BINARY (Continues…)
99 – (71)
99 + (-71) = 28
128 64 32 16 8 4 2 1
0 1 1 0 0 0 1 1 = 99
0 1 0 0 0 1 1 1 = 71
1 0 1 1 1 0 0 0 = 71’s 1’s comp.
1
+
1 0 1 1 1 0 0 1 = 71’s 2’s comp.
0 1 1 0 0 0 1 1 = 99
1 0 1 1 1 0 0 1 = 71’s 2’s comp.
+
(1) 0 0 0 1 1 1 0 0 = 28
An overflow as occurred

## Slide 47: PERT Chart
Question two [25 Marks]
Mitigation and Remediation require planning in advance. PERT can be used to visualize these plans and make it easy for IT and Project Managers to follow through.
Construct a network diagram with the data given below. [5 Marks]

## Slide 48: PERT Chart (Continues…)
PERT Chart
Activities | Dependencies | Duration (Days)
A |  | 5
B |  | 3
C | A | 10
D | B | 2
E | C,D | 6
A
B
(2)
D
E
1
2
3
4
5
(5)
(10)
(6)
(3)
C
0
5
3
15
21
0
5
15
13
21
Slack = 0
Slack = 0
Slack = 0
Slack = 0
Slack = 10

## Slide 49: PERT Chart (Continues…)
Compute the Project duration. [2 Marks]
Determine the critical path. [10 Marks]
Draw a project network for a remediation plan from the following statement E > B, C; F, G > D; H,I > E, F; J > I, G; K > H; B > A;. [8 Marks]
Duration of The Project = 5 + 10 + 6
= 21 Days
Critical Path (CMP) = 1 – 2 – 4 – 5

## Slide 50: PERT Chart (Continues…)
.
Activities | Predecessors
A | 
B | A
C | 
D | 
E | B, C
F | D
G | D
H | E, F
I | E, F
J | I, G
K | H
1
2
3
4
5
6
7
8
A
B
C
D
E
F
G
H
I
J
K

## Slide 51: PERT Chart (Continues…)
Question Three [25 Marks]
Activities of a remediation plan has been assigned to you to come up with the project network which is scheduled to be presented in a managing meeting.
Draw a network diagram for the remediation plan project. [5 Marks]

## Slide 52: PERT Chart (Continues…)
Activities | Duration
1 – 2 | 13
1 – 3 | 12
2 – 4 | 2
3 – 4 | 8
2 – 5 | 15
4 – 5 | 2
1
2
3
5
4
2
13
12
2
8
5
15
13
12
28
20
26
28
18
13
0
0
Slack = 0
Slack = 0
Slack = 6
Slack = 6
Slack = 0

## Slide 53: PERT Chart (Continues…)
Determine the critical path and find the Earliest Start (ES), Earliest Finish (EF), Latest Start (LS), and Latest Finish (LF) Time. [10 Marks]
Critical Path = 1 – 2 – 5

## Slide 54: PERT Chart (Continues…)
Activities | ES | Duration | EF (ES + D)
1 – 2 | 0 | 13 | 13
1 – 3 | 0 | 12 | 12
2 – 4 | 13 | 2 | 15
3 – 4 | 12 | 8 | 20
2 – 5 | 13 | 15 | 28
4 – 5 | 20 | 2 | 22
Activities | LF | Duration | LS (LF - D)
1 – 2 | 13 | 13 | 0
1 – 3 | 18 | 12 | 6
2 – 4 | 26 | 2 | 24
3 – 4 | 26 | 8 | 18
2 – 5 | 28 | 15 | 13
4 – 5 | 28 | 2 | 26
LS | ES | TF (LS - ES)
0 | 0 | 0
6 | 0 | 6
24 | 13 | 11
18 | 12 | 6
13 | 13 | 0
26 | 20 | 6

## Slide 55: PERT Chart (Continues…)
Calculate the Total Float (TF), Free Float (FF), Independent Float (IND F), and the Interfering Float (INT F). [10 Marks]

## Slide 56: PERT Chart (Continues…)
Activities | T | H | TF | FF (TF – H) | IND F (FF – T) | INT F (TF – FF)
1 – 2 | 0 | 0 | 0 | 0 | 0 | 0
1 – 3 | 0 | 6 | 6 | 0 | 0 | 6
2 – 4 | 0 | 6 | 11 | 5 | 5 | 6
3 – 4 | 6 | 6 | 6 | 0 | -6 | 6
2 – 5 | 0 | 0 | 0 | 0 | 0 | 0
4 – 5 | 6 | 0 | 6 | 6 | 0 | 0

## Slide 57: PERT Chart (Continues…)
Question four [25 Marks]
The following have been given for your convenient as an IT Manager in charge of all ICT work related project.
.
Activity | Optimistic (O or to) | Pessimistic (P or tp) | Most Likely (M or tm)
1 – 2 | 3 | 15 | 6
2 – 3 | 2 | 14 | 5
1 – 4 | 6 | 30 | 12
2 – 5 | 2 | 8 | 5
2 – 6 | 5 | 17 | 11
3 – 6 | 3 | 15 | 6
4 – 7 | 3 | 27 | 9
5 – 7 | 1 | 7 | 4
6 – 7 | 2 | 8 | 5

## Slide 58: PERT Chart (Continues…)
Draw the corresponding network diagram.

## Slide 59: PERT Chart (Continues…)
Compute the expected duration for each activity. [5 Marks]
.
4tm | Te = to + 4tm + tp
4(6) = 24 | (3 + 24 + 15) / 6 = 7
4(5) = 20 | (2 + 20 + 14) / 6 = 6
4(12) = 48 | (6 + 48 + 30) / 6 = 14
4(5) = 20 | (2 + 20 + 8) / 6 = 5
4(11) = 44 | (5 + 44 + 17) / 6 = 11
4(6) = 24 | (3 + 24 + 15) / 6 = 7
4(9) = 36 | (3 + 36 + 27) / 6 = 11
4(4) = 16 | (1 + 16 + 7) / 6 = 4
4(5) = 20 | (2 + 20 + 8) / 6 = 5

## Slide 60: PERT Chart (Continues…)
Calculate the expected variance of each activity. [5 Marks]
σ = (tp – to) / 6
(15 – 3) / 6 = 2
(14 – 2) / 6 = 2
(30 – 6) / 6 = 4
(8 – 2) / 6 = 1
(17 – 5) / 6 = 2
(15 – 3) / 6 = 2
(27 – 3) / 6 = 4
(7 – 1) / 6 = 1
(8 – 2) / 6 = 1

## Slide 61: PERT Chart (Continues…)
Determine the expected critical path variance. [5 Marks]
Compute the standard deviation of each activity. [5 Marks]
Critical Path = 1 – 4 – 7
Critical Variance = 16 + 16
= 32
σ²
4
4
16
1
4
4
16
1
1